## 1st Quarter
FDP Form No. 6 - Trust Fund Utilitzation
CONSOLIDATED QUARTERLY REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
FOR THE 1ST QUARTER CY 2023
PROVICE OF MISAMIS OCCIDENTAL |  | City of Tangub
PROGRAM OR TARGET | LOCATION | TOTAL FUNDS AVAILABLE (COST) | DATE STARTED (RECEIPT) | TARGET DATE OF COMPLETION | PROJECT STATUS |  | NO. OF EXTENTIONS, IF ANY | COUNTERPART, IF ANY |  | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date |  | FUND TRANSFERRED | COST CHARGED
CHED
CHED - TERTIARY EDUC. SUPPORT PROG. | GADTC | 97913527.51 | 2020-02-11 |  | 83.31% | 81575502.42
DA
DA - COB DRYER |  | 150000 |  |  | 0%
DA - NAPC COMMUNITY FOOD PRODUCTION |  | 1025729 | 2017-05-02 |  | 91.78% | 941398.43
DA BUB 2014 - ESTABLIHSMENT OF DOCKING AREA |  | 760000 | 2018-11-21 |  | 100% | 760000
DA BUB 2014 - FISHERY PROJECTS |  | 1375580 | 2017-05-02 |  | 49.33% | 678533
DA BUB 2015 - ESTABLISHMENT OF FISH IN CAGES TECHNO DEMO PROJ. |  | 2787498 | 2017-11-17 |  | 80.35% | 2239640
DA BUB PROJ. - SUSTAINABLE AGRI-FISHERY LIVELIHOOD |  | 880000 | 2018-06-14 |  | 99.83% | 878528
DA/BFAR - COMMUNITY FISH LANDING |  | 3000000 | 2017-12-07 |  | 97% | 2910000
DA - FMR (5 BARANGAYS) |  | 1516900 | 2020-01-31 |  | 71.6% | 1086093.35
REG 10 GPBP PROJECTS |  | 1379000 | 2023-03-08 |  | 0% | 0
REG 10 PAITON-BINTANA-SICOT FMR |  | 323994 | 2023-03-08 |  | 0% | 0
SPRING DEV'T & FARM RESERVOIR-LPRAP BUB |  | 75000 | 2023-03-08 |  | 0% | 0
DENR - MRF SUPPORT FUND |  | 332500 | 2018-05-31 |  | 57.14% | 190000
DOH
DOH - CAPITATION FUND |  | 3980380.24 | 2017-05-02 |  | 67.86% | 2701177.8
DOH - REVOLVING FUND |  | 10801730.53 | 2017-05-02 |  | 100% | 10801730.53
DOH - BHS HFEP 2020-Repair/Renovation | MANGA | 1000000 | 2022-02-21 |  | 0% | 0
DOH-ONE COVID ALLOWANCE 2022 |  | 864000 | 2022-11-16 |  | 100% | 864000
DOH-NATIONAL NUTRITION COUNCIL |  | 79000 | 2022-10-01 |  | 100% | 79000
DOLE
TUPAD |  | 20576400 | 2022-12-09 |  | 0% | 0
DOT
DOT - FINANCIAL ASSISTANCE TO CHRISTMAS SYMBOL |  | 12412.74 | 2017-05-02 |  | 0% | 0
DOT - FINANCIAL ASSISTANCE TO SCC |  | 29896.17 | 2017-05-02 |  | 0% | 0
DOT - TIEZA (IMPROVEMENT OF BELVEDERE) | FERTIG HILLS | 4242749.65 | 2017-05-02 |  | 58.53% | 2483256.46
DOST
DOST-FINANCIAL ASSISTANCE FOR FNRI ELCAC |  | 785135 | 2021-12-23 |  | 83.11% | 652518
DPWH
DPWH - CANIANGAN FMR | CANIANGAN | 9951000 | 2017-05-02 |  | 80.45% | 8005428.02
DPWH - CONCRETING OF LORENZO TAN ROAD | LORENZO TAN | 64561.84 | 2017-05-02 |  | 0% | 0
DPWH - SLRF |  | 180342.5 | 2017-05-02 |  | 0% | 0
DPWH - SLRF 2011 (OPEN CANAL GOMEZ ST.) | GOMEZ ST. | 350878.4 | 2017-05-02 |  | 91.1% | 319653
DSWD
DSWD - AICS | CSWD | 1600000 | 2017-05-12 |  | 100% | 1600000
DSWD - CONVERSION OF 10 DAY CARE CENTERS | CSWD | 1000000 | 2017-05-02 |  | 100% | 1000000
DSWD - DAY CARE CONSTRUCTION | LORENZO TAN | 800000 | 2018-12-28 |  | 100% | 800000
DSWD - SOCIAL PENSION FUND | CSWD | 2307000 | 2017-05-02 |  | 100% | 2307000
DSWD - SUPPLEMENTAL FEEDING | CSWD | 2685787.6 | 2017-05-02 |  | 100% | 2685787.6
DTI
DTI - BUB DTI LIVELIHOOD CAPABILITY BLDG. PROGRAM |  | 1065703.02 | 2017-05-02 |  | 46.42% | 494671
DTI - SMALL & MEDIUM SCALE ENT. |  | 517754.38 | 2017-05-02 |  | 0% | 0
DTI - SOCIO ECONOMIC LIVELIHOOD PROJ |  | 114152.53 | 2017-05-02 |  | 0% | 0
IMPROVEMENT OF SCC |  | 2305581.76 | 2017-05-02 |  | 0% | 0
LGSF
LGSF - BATCH 70 | PANGABUAN-GUINALABAN | 3000000 | 2018-09-18 |  | 100% | 3000000
LGSF - BATCH 6 - TANGUB CITY BOULEVARD | MALORO-SILANGA | 7381602 | 2019-03-06 |  | 100% | 7381602
LGSF - BATCH 24 - AICS | TANGUB | 871394.01 | 2019-03-06 |  | 100% | 871394.01
LGSF - BATCH 94 - MULTI PURPOSE BLDG | MIGCANAWAY | 20000000 | 2019-02-12 |  | 93.74% | 18748007.81
LGSF- FMR LABUYO | LABUYO | 10000000 | 2020-05-08 |  | 100% | 10000000
LGSF-CONSTRUCTION OF BOULEVARD (BAYWALK PHASE II) | MALORO-MIGCANAWAY | 13867875 | 2020-12-01 |  | 54.8% | 7599522.99
LGSF-Concreting of Road Going to Purok 3/ 5.0 meters wide, 0.20m thickness and 150 linear meters long | OWAYAN | 3000000 | 2021-05-05 |  | 0% | 0
LGSF-Construction of Additional Water System (Piping and Site Development) | OWAYAN | 1000000 | 2021-05-05 |  | 0% | 0 |  | 821482.75
LGSF-Concreting of Road to Matugnao | OWAYAN | 16000000 | 2021-05-05 |  | 53.9% | 8623985.33
LGSF-Completion of 1 Lane Road (From Purok 2 to Taguite Boundary) | SAN ANTONIO | 5000000 | 2021-05-05 |  | 0% | 0
LGSF-Concreting of 2-Lane Road (Purok 1 & 3) | SAN ANTONIO | 12000000 | 2021-05-05 |  | 54.87% | 6584348.71
LGSF-Concreting of Road beside San Antonio Elementary School | SAN ANTONIO | 2000000 | 2021-05-05 |  | 0% | 0
LGSF-Expansion of Water System at Purok 2 | SAN ANTONIO | 1000000 | 2021-05-05 |  | 100% | 3173107.8 |  | 2173107.8
LGSF-Concreting of Road at Purok 3, with cross drainage | SICOT | 5000000 | 2021-05-05 |  | 100% | 5000000
LGSF-Concreting of Road from (Purok 2,5-6) | SICOT | 10000000 | 2021-05-05 |  | 100% | 10000000
LGSF-Construction of Water System with Reservoir from Purok 1-6 | SICOT | 5000000 | 2021-05-05 |  | 67.81% | 3390626.98
LGSF-Construction of Tangub City Boulevard (baywalk Development) Phase III | MALORO-SILANGA | 14258691 | 2021-07-19 |  | 0% | 0
LGSF-Assistance program and project for education, health and social protection in light of the COVID-19 Pandemic (Purchase of Mobile Devices) | TANGUB | 20000000 | 2022-02-24 |  | 100% | 20000000
LGSF GEF-Livelihood Assistance Program | TANGUB | 7000000 | 2022-08-10 |  | 99.29% | 6950000
LGSF GEF-Financial Assistance (AICS and Other Support Program) | TANGUB | 5995860 | 2022-08-10 |  | 26.62% | 1595926.45
LGSF GEF-Construction of Water System | TANGUB | 10000000 | 2022-08-10 |  | 0% | 0
LGSF GEF-Supply and Delivery of Various Agricultural and Aquacultural Products and Materials | TANGUB | 5000000 | 2022-08-10 |  | 0% | 0 |  | 3000000
LGSF GEF-Purchase of Medicines | TANGUB | 1000000 | 2022-08-10 |  | 0% | 0
LGSF SBDP 2022-Installation of Solar Post and Lamps Solar Lights (Solar Street Lights with Complete Accessories) | TANGUB | 1500000 | 2022-10-06 |  | 0% | 0
LGSF SBDP 2022-Construction of 64 cu.m. water tyank, source development and provision of distribution lines/pipes | TANGUB | 2500000 | 2022-10-06 |  | 0% | 0
LGSF SBDP 2022-Rehabilitation of Sto. Niño Elementary School Buildings and Rehabilitation of other facilities and structures | STO. NIÑO | 3000000 | 2022-10-06 |  | 0% | 0
LGSF SBDP 2022- Installation of solar post and lamps solar lights (solar st. lights with complete accessories) Brgy Sto. Niño | STO. NIÑO | 1000000 | 2022-10-06 |  | 0% | 0
NHA
NHA-Panguil Bay Residences | BALATACAN | 25000000 | 2022-02-11 |  | 100% | 25000000
PHILHEALTH
PHILHEALTH - DRUGS AND MEDICINES |  | 202196.65 | 2017-05-02 |  | 0% | 0
PHILHEALTH - REAGENTS, SUPPLIES AND EQUIPMENT |  | 1082635.15 | 2017-05-02 |  | 0% | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness
of the data or information contained in this document.
Sgd. ANNA RUTCHEL M. OLEGARIO, CPA |  |  |  |  | Sgd. SABINIANO S. CANAMA
City Accountant |  |  |  |  | City Mayor